## Sheet1
PROJECT TITLE |  | OK! Food Delivery Data Warehouse
TEAM |  | 2
NO | TASK | PIC | STATUS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  |  |  | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23
1 | Project Initiation Document | Dika | Complete | bar: WEEK 1 31 to WEEK 1 2
2 | Gantt Chart | Dika | Complete | bar: WEEK 1 1 to WEEK 1 2
3 | Part 1: Entity Relationship Diagram | Fine | Complete | bar: WEEK 2 5
4 | Part 2: SQL and Database | Fine | Complete | bar: WEEK 2 6
5 | Part 3: Exploratory Data Analysis | Fine | Complete | bar: WEEK 2 7
6 | Part 4: ETL dan Scheduled Job | Dika | Complete | bar: WEEK 2 8
7 | Part 5: Revenue & Customer Monitoring | Dika | Complete | bar: WEEK 2 9 to WEEK 3 14
8 | User Manual & User Testing | Dika | Complete | bar: WEEK 3 14 to WEEK 3 16
9 | Dashboard | Fine | Complete | bar: WEEK 3 15 to WEEK 3 16
10 | Final Presentation | Fine | Complete | bar: WEEK 4 19 to WEEK 4 20

## Copy of Sheet1
PROJECT TITLE |  | OK! Food Delivery Data Warehouse
TEAM |  | 2
NO | TASK | PIC | STATUS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  |  |  | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23
1 | Project Initiation Document | Dika | bar: WEEK 1 31 to WEEK 1 2
2 | Gantt Chart | Dika | bar: WEEK 1 1 to WEEK 1 2
3 | Part 1: Entity Relationship Diagram | Fine | bar: WEEK 2 5
4 | Part 2: SQL and Database | Fine | bar: WEEK 2 6
5 | Part 3: Exploratory Data Analysis | Fine | bar: WEEK 2 7
6 | Part 4: ETL dan Scheduled Job | Dika | bar: WEEK 2 8
7 | Part 5: Revenue & Customer Monitoring | Dika | bar: WEEK 2 9 to WEEK 3 14
8 | User Manual & User Testing | Dika | bar: WEEK 3 14 to WEEK 3 16
9 | Dashboard | Fine | bar: WEEK 3 15 to WEEK 3 16
10 | Final Presentation | Fine | bar: WEEK 4 19 to WEEK 4 20